## 1212 (W13)
Group 2 Meeting Minutes
Date |  | 2023/12/09, 2023/12/12
Time |  | 19:00-19:30, 19:00-20:10
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論本週作業、分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- Discuss term project (system overview, important code design & class diagram, WBS including LOC, estimated/actual effort) - Term project presentation rehersal - Discuss code tracing issue
Group |  | Slide URL
Term Project |  | https://docs.google.com/presentation/d/1WEzksak5OHnIjlEZQx2vjcU88P8CcXn9Xybty00FstA/edit#slide=id.p
WBS |  | WBS
Jira Board |  | https://leon1234858.atlassian.net/jira/software/projects/SPRING/boards/1
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note (not Closed?)
W13-1 | Code tracing: See WBS W13 |  |  | 許庭瑋 | 2023-12-14 08:00 | Closed
W13-2 | Code tracing: See WBS W13 |  |  | 洪世彬 | 2023-12-14 08:00 | Closed
W13-3 | Code tracing: See WBS W13 |  |  | 劉玠均 | 2023-12-14 08:00 | Closed
W13-4 | Code tracing: See WBS W13 |  |  | 楊昕叡 | 2023-12-14 08:00 | Closed
W13-5 | Code tracing: See WBS W13 |  |  | 林俊佑 | 2023-12-14 08:00 | Closed
W13-6 | Code tracing: See WBS W13 |  |  | 陳君翰 | 2023-12-14 08:00 | Closed
W13-7 | Term project: discuss system overview (cross module interactions) |  |  | all | 2023-12-12 20:00 | Closed
W13-8 | Term project: prepare slide |  |  | all | 2023-12-12 20:00 | Closed
W13-9 | Exam place and all related issues |  |  | 林俊佑 | 2023-12-21 07:00 | Open
W13-10 | Term project: system overview (spring-core) |  |  | 洪世彬 | 2023-12-12 20:00 | Closed
W13-11 | Term project: system overview (aot, cglib) |  |  | 林俊佑 | 2023-12-12 20:00 | Closed
W13-10 | Collect course feedback |  |  | 許庭瑋 | 2023-12-21 07:00 | Open
W11-1 | Code tracing: See WBS W11 |  |  | 許庭瑋 | 2023-11-30 08:00 | Closed
W11-2 | Code tracing: See WBS W11 |  |  | 洪世彬 | 2023-11-30 08:00 | Closed
W11-3 | Code tracing: See WBS W11 |  |  | 劉玠均 | 2023-11-30 08:00 | Closed
W11-4 | Code tracing: See WBS W11 |  |  | 楊昕叡 | 2023-11-30 08:00 | Closed
W11-5 | Code tracing: See WBS W11 |  |  | 林俊佑 | 2023-11-30 08:00 | Closed
W11-6 | Code tracing: See WBS W11 |  |  | 陳君翰 | 2023-11-30 08:00 | Closed
W11-7 | Complete weekly slides and homework/design |  |  | all | 2023-11-30 08:00 | Closed
W11-8 | Upload HW1-PrintOut (jira) |  |  | 林俊佑 | 2023-11-30 08:00 | Closed
W11-9 | Upload HW2-SchematicCaptureSystems (jira) |  |  | 劉玠均 | 2023-11-30 08:00 | Closed
W11-10 | Upload HW3-EmailHandler (jira) |  |  | 楊昕叡 | 2023-11-30 08:00 | Closed
W11-11 | Upload HW4-WindowFramework (jira) |  |  | 陳君翰 | 2023-11-30 08:00 | Closed
W11-12 | Summarize HW0-1: Thread Pool (jira) |  |  | 許庭瑋 | 2023-11-30 08:00 | Closed
W11-13 | Summarize HW0-2: ImmutableObject (jira) |  |  | 洪世彬 | 2023-11-30 08:00 | Closed
W10-1 | Code tracing: See WBS W10 |  |  | 許庭瑋 | 2023-11-23 08:00 | Closed
W10-2 | Code tracing: See WBS W10 |  |  | 洪世彬 | 2023-11-23 08:00 | Closed
W10-3 | Code tracing: See WBS W10 |  |  | 劉玠均 | 2023-11-23 08:00 | Closed
W10-4 | Code tracing: See WBS W10 |  |  | 楊昕叡 | 2023-11-23 08:00 | Closed
W10-5 | Code tracing: See WBS W10 |  |  | 林俊佑 | 2023-11-23 08:00 | Closed
W10-6 | Code tracing: See WBS W10 |  |  | 陳君翰 | 2023-11-23 08:00 | Closed
W10-7 | Complete weekly slides and homework/design |  |  | all | 2023-11-23 08:00 | Closed
W10-8 | Upload HW1 (jira) |  |  | 劉玠均 | 2023-11-21 19:00 | Closed
W10-9 | Upload HW2 (jira) |  |  | 林俊佑 | 2023-11-21 19:00 | Closed
W10-10 | Upload HW3 (jira) |  |  | 洪世彬 | 2023-11-21 19:00 | Closed
W10-11 | Summarize answer to "Can we add duplicate responsibilities? (8-1, p.20)" |  |  | 陳君翰 | 2023-11-21 19:00 | Closed
W9-1 | Code tracing: See WBS W9 |  |  | 許庭瑋 | 2023-11-16 08:00 | Closed
W9-2 | Code tracing: See WBS W9 |  |  | 洪世彬 | 2023-11-16 08:00 | Closed
W9-3 | Code tracing: See WBS W9 |  |  | 劉玠均 | 2023-11-16 08:00 | Closed
W9-4 | Code tracing: See WBS W9 |  |  | 楊昕叡 | 2023-11-16 08:00 | Closed
W9-5 | Code tracing: See WBS W9 |  |  | 林俊佑 | 2023-11-16 08:00 | Closed
W9-6 | Code tracing: See WBS W9 |  |  | 陳君翰 | 2023-11-16 08:00 | Closed
W9-7 | Complete weekly slides |  |  | all | 2023-11-16 08:00 | Closed
W8-1 | Code tracing: See WBS W8 |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W8-2 | Code tracing: See WBS W8 |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-3 | Code tracing: See WBS W8 |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-4 | Code tracing: See WBS W8 |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-5 | Code tracing: See WBS W8 |  |  | 林俊佑 | 2023-11-09 08:00 | Closed
W8-6 | Code tracing: See WBS W8 |  |  | 陳君翰 | 2023-11-09 08:00 | Closed
W8-7 | Complete weekly slides (code tracing) and homework/design |  |  | all | 2023-11-09 08:00 | Closed
W8-8 | Upload HW1 (jira) |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-9 | Upload HW2 (jira) |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-10 | Summarize Dependency Injection (jira) |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-11 | Create Gitlab group account |  |  | 林俊佑 | 2023-11-09 08:00 | Suspend
W8-12 | Exam place and all related issues |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W7-1 | Code tracing: See WBS W7 |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W7-2 | Code tracing: See WBS W7 |  |  | 洪世彬 | 2023-11-02 08:00 | Closed
W7-3 | Code tracing: See WBS W7 |  |  | 劉玠均 | 2023-11-02 08:00 | Closed
W7-4 | Code tracing: See WBS W7 |  |  | 楊昕叡 | 2023-11-02 08:00 | Closed
W7-5 | Code tracing: See WBS W7 |  |  | 林俊佑 | 2023-11-02 08:00 | Closed
W7-6 | Code tracing: See WBS W7 |  |  | 陳君翰 | 2023-11-02 08:00 | Closed
W7-7 | Complete weekly slides (code tracing) |  |  | all | 2023-11-02 08:00 | Closed
W7-8 | Homework 0-2 (P83-P85) (jira) |  |  | all | 2023-11-01 20:00 | Closed
W7-9 | Complete inner class slide |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W6-1 | Code tracing: See WBS W6 |  |  | 許庭瑋 | 2023-10-26 08:00 | Closed
W6-2 | Code tracing: See WBS W6 |  |  | 洪世彬 | 2023-10-26 08:00 | Closed
W6-3 | Code tracing: See WBS W6 |  |  | 劉玠均 | 2023-10-26 08:00 | Closed
W6-4 | Code tracing: See WBS W6 |  |  | 楊昕叡 | 2023-10-26 08:00 | Closed
W6-5 | Code tracing: See WBS W6 |  |  | 林俊佑 | 2023-10-26 08:00 | Closed
W6-6 | Code tracing: See WBS W6 |  |  | 陳君翰 | 2023-10-26 08:00 | Closed
W6-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-26 08:00 | Closed
W6-8 | 在 JIRA 新增自己的 issues |  |  | all | 2023-10-26 08:00 | Closed
W5-1 | Code tracing: See WBS W5 |  |  | 許庭瑋 | 2023-10-19 08:00 | Closed
W5-2 | Code tracing: See WBS W5 |  |  | 洪世彬 | 2023-10-19 08:00 | Closed
W5-3 | Code tracing: See WBS W5 |  |  | 劉玠均 | 2023-10-19 08:00 | Closed
W5-4 | Code tracing: See WBS W5 |  |  | 楊昕叡 | 2023-10-19 08:00 | Closed
W5-5 | Code tracing: See WBS W5 |  |  | 林俊佑 | 2023-10-19 08:00 | Closed
W5-6 | Code tracing: See WBS W5 |  |  | 陳君翰 | 2023-10-19 08:00 | Closed
W5-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-19 08:00 | Closed
W4-1 | WBS: 列出到 W13 的時間規劃 |  |  | all | 2023-10-12 08:00 | Closed
W4-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 12:00 | Closed
W4-3 | Code tracing: AbstractFileResolvingResource.java, ClassPathResource.java, UrlResource.java, ResourceUtils.java |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed
W4-4 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-12 08:00 | Closed
W4-5 | Code tracing: ConvertingComparator<S, T>, DefaultConversionService, 8 default converters |  |  | 劉玠均 | 2023-10-12 08:00 | Closed
W4-6 | Code tracing: AnnotationsScanner.java, AttributeMethods.java |  |  | 楊昕叡 | 2023-10-12 08:00 | Closed
W4-7 | Code tracing: spring-core-cglib |  |  | 林俊佑 | 2023-10-12 08:00 | Closed
W4-8 | Code tracing: aot.generate |  |  | 陳君翰 | 2023-10-12 08:00 | Closed
W4-9 | Complete weekly slides (整合 HW4 & HW5 答案 & code tracing） |  |  | all | 2023-10-12 08:00 | Closed
W3-1 | 重新定 code tracing 分工: spring-core-core |  |  | all | 2023-09-28 | Closed
W3-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed | moved to next week
W3-3 | 依新分工調整 WBS (LOC, responsibility, effort) |  |  | all | 2023-10-03 19:00 | Closed
W3-4 | Survey issue tracking system |  |  | all | 2023-10-03 19:00 | Closed
W3-5 | 釐清 W4 presentation focus、progress report |  |  | 許庭瑋 | 2023-10-03 19:00 | Closed
W3-6 | 確定 spring-core-core others 細部分工 |  |  | 劉玠均、洪世彬 | 2023-09-29 | Closed
W3-7 | 確定 spring-core-aot, spring-core-cglib 細部分工 |  |  | 林俊佑、陳君翰 | 2023-10-03 | Closed
W3-8 | Code tracing: spring-core-io |  |  | 許庭瑋 | 2023-10-05 08:00 | Closed
W3-9 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-05 08:00 | Closed
W3-10 | Code tracing: W3 in WBS (i.e., spring-core converter/*.java, GenericConversionService.java) |  |  | 劉玠均 | 2023-10-05 08:00 | Closed
W3-11 | Code tracing:W3 in WBS |  |  | 楊昕叡 | 2023-10-05 08:00 | Closed
W3-12 | Code tracing: spring-core-cglib 內 proxy |  |  | 林俊佑 | 2023-10-05 08:00 | Closed
W3-13 | Code tracing: spring-core-cglib 內 proxy |  |  | 陳君翰 | 2023-10-05 08:00 | Closed
W3-14 | Complete JIRA slides |  |  | 林俊佑、洪世彬 | 2023-10-05 08:00 | Closed
W3-15 | Complete weekly slides |  |  | all | 2023-10-05 08:00 | Closed
W2-1 | Code tracing 分工 |  |  | All | 2023-09-24 | Closed
W2-2 | Complete week 2 slide |  |  | All | 2023-09-25 20:00 | Closed
W2-3 | 釐清 WBS 書寫方式 |  |  | 許庭瑋 | 2023-09-28 08:00 | Closed
W2-4 | 看spring-expression的code |  |  | 許庭瑋 | 2023-12-21 | Suspend | focus on Spring-Core
W2-5 | 看spring-core-aot….的code |  |  | 陳君翰 | 2023-12-21 | Suspend
W2-6 | 看spring-beans的code |  |  | 洪世彬 | 2023-12-21 | Suspend
W2-7 | 看spring-core-core-annotation …的code |  |  | 劉玠均 | 2023-12-21 | Suspend
W2-8 | 看spring-context的code |  |  | 楊昕叡 | 2023-12-21 | Suspend
W2-9 | 看spring-core-cglib, spring-core-asm的code |  |  | 林俊佑 | 2023-12-21 | Suspend
W1-1 | Survey Spring Boot |  |  | 許庭瑋 | 2023-09-19 | Closed
W1-2 | Survey Spring Cloud |  |  | 陳君翰 | 2023-09-19 | Closed
W1-3 | Survey Spring Framework - Core Container |  |  | 劉玠均 | 2023-09-19 | Closed
W1-4 | Survey Spring Framework - AOP |  |  | 楊昕叡 | 2023-09-19 | Closed
W1-5 | Survey Spring Framework - Data Access/Integration |  |  | 洪世彬 | 2023-09-19 | Closed
W1-6 | Survey Spring Framework - Web (MVC/Remoting) |  |  | 林俊佑 | 2023-09-19 | Closed
W1-7 | Summarize Spring components in the slide |  |  | All | 2023-09-20 20:00 | Closed
W1-8 | Complete AOP slide |  |  | 楊昕叡 | 2023-09-20 20:00 | Closed
W1-9 | Complete ORM / JDBC slide |  |  | 洪世彬 | 2023-09-20 20:00 | Closed

## 1205 (W12)
Group 2 Meeting Minutes
Date |  | 2023-12-05
Time |  | 19:00-20:00
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論本週作業、分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- Discuss code tracing issue & homework designs, issue: \ No newline at end of file, Visitor pattern (HW4 and code tracing) - Discuss term project (system overview, important code design & class diagram, WBS including LOC, estimated/actual effort)
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1raLD82B9BUycqq6iJB_vMbtv4EIDUPEcjKNv9Ik3OyE/edit#slide=id.p
WBS |  | WBS
Jira Board |  | https://leon1234858.atlassian.net/jira/software/projects/SPRING/boards/1
Term Project (WIP) |  | https://docs.google.com/presentation/d/1WEzksak5OHnIjlEZQx2vjcU88P8CcXn9Xybty00FstA/edit#slide=id.p
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note (not Closed?)
W12-1 | Code tracing: See WBS W12 |  |  | 許庭瑋 | 2023-12-07 08:00 | Closed
W12-2 | Code tracing: See WBS W12 |  |  | 洪世彬 | 2023-12-07 08:00 | Closed
W12-3 | Code tracing: See WBS W12 |  |  | 劉玠均 | 2023-12-07 08:00 | Closed
W12-4 | Code tracing: See WBS W12 |  |  | 楊昕叡 | 2023-12-07 08:00 | Closed
W12-5 | Code tracing: See WBS W12 |  |  | 林俊佑 | 2023-12-07 08:00 | Closed
W12-6 | Code tracing: See WBS W12 |  |  | 陳君翰 | 2023-12-07 08:00 | Closed
W12-7 | Complete weekly slides and homework/design |  |  | all | 2023-12-07 08:00 | Closed
W12-8 | Upload HW1-ProgrammingEnvironment (jira) |  |  | 楊昕叡 | 2023-12-07 08:00 | Closed
W12-9 | Upload HW2-CutCopyPaste (jira) |  |  | 劉玠均 | 2023-12-07 08:00 | Closed
W12-10 | Upload HW3-DocumentViewerApplication (jira) |  |  | 陳君翰、林俊佑 | 2023-12-07 08:00 | Closed
W12-11 | Upload HW4-AST (jira) |  |  | 洪世彬 | 2023-12-07 08:00 | Closed
W12-12 | Term project: discuss system overview (cross module interactions) |  |  | all | 2023-12-14 08:00 | Open
W12-13 | Term project: prepare slide |  |  | all | 2023-12-14 08:00 | Open
W12-14 | Exam place and all related issues |  |  | 林俊佑 | 2023-12-21 07:00 | Open
W12-14 | Term project: system overview (spring-core) |  |  | 洪世彬 | 2023-12-18 19:00 | Open
W12-15 | Term project: system overview (aot, cglib) |  |  | 林俊佑 | 2023-12-18 19:00 | Open
W11-1 | Code tracing: See WBS W11 |  |  | 許庭瑋 | 2023-11-30 08:00 | Closed
W11-2 | Code tracing: See WBS W11 |  |  | 洪世彬 | 2023-11-30 08:00 | Closed
W11-3 | Code tracing: See WBS W11 |  |  | 劉玠均 | 2023-11-30 08:00 | Closed
W11-4 | Code tracing: See WBS W11 |  |  | 楊昕叡 | 2023-11-30 08:00 | Closed
W11-5 | Code tracing: See WBS W11 |  |  | 林俊佑 | 2023-11-30 08:00 | Closed
W11-6 | Code tracing: See WBS W11 |  |  | 陳君翰 | 2023-11-30 08:00 | Closed
W11-7 | Complete weekly slides and homework/design |  |  | all | 2023-11-30 08:00 | Closed
W11-8 | Upload HW1-PrintOut (jira) |  |  | 林俊佑 | 2023-11-30 08:00 | Closed
W11-9 | Upload HW2-SchematicCaptureSystems (jira) |  |  | 劉玠均 | 2023-11-30 08:00 | Closed
W11-10 | Upload HW3-EmailHandler (jira) |  |  | 楊昕叡 | 2023-11-30 08:00 | Closed
W11-11 | Upload HW4-WindowFramework (jira) |  |  | 陳君翰 | 2023-11-30 08:00 | Closed
W11-12 | Summarize HW0-1: Thread Pool (jira) |  |  | 許庭瑋 | 2023-11-30 08:00 | Closed
W11-13 | Summarize HW0-2: ImmutableObject (jira) |  |  | 洪世彬 | 2023-11-30 08:00 | Closed
W10-1 | Code tracing: See WBS W10 |  |  | 許庭瑋 | 2023-11-23 08:00 | Closed
W10-2 | Code tracing: See WBS W10 |  |  | 洪世彬 | 2023-11-23 08:00 | Closed
W10-3 | Code tracing: See WBS W10 |  |  | 劉玠均 | 2023-11-23 08:00 | Closed
W10-4 | Code tracing: See WBS W10 |  |  | 楊昕叡 | 2023-11-23 08:00 | Closed
W10-5 | Code tracing: See WBS W10 |  |  | 林俊佑 | 2023-11-23 08:00 | Closed
W10-6 | Code tracing: See WBS W10 |  |  | 陳君翰 | 2023-11-23 08:00 | Closed
W10-7 | Complete weekly slides and homework/design |  |  | all | 2023-11-23 08:00 | Closed
W10-8 | Upload HW1 (jira) |  |  | 劉玠均 | 2023-11-21 19:00 | Closed
W10-9 | Upload HW2 (jira) |  |  | 林俊佑 | 2023-11-21 19:00 | Closed
W10-10 | Upload HW3 (jira) |  |  | 洪世彬 | 2023-11-21 19:00 | Closed
W10-11 | Summarize answer to "Can we add duplicate responsibilities? (8-1, p.20)" |  |  | 陳君翰 | 2023-11-21 19:00 | Closed
W9-1 | Code tracing: See WBS W9 |  |  | 許庭瑋 | 2023-11-16 08:00 | Closed
W9-2 | Code tracing: See WBS W9 |  |  | 洪世彬 | 2023-11-16 08:00 | Closed
W9-3 | Code tracing: See WBS W9 |  |  | 劉玠均 | 2023-11-16 08:00 | Closed
W9-4 | Code tracing: See WBS W9 |  |  | 楊昕叡 | 2023-11-16 08:00 | Closed
W9-5 | Code tracing: See WBS W9 |  |  | 林俊佑 | 2023-11-16 08:00 | Closed
W9-6 | Code tracing: See WBS W9 |  |  | 陳君翰 | 2023-11-16 08:00 | Closed
W9-7 | Complete weekly slides |  |  | all | 2023-11-16 08:00 | Closed
W8-1 | Code tracing: See WBS W8 |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W8-2 | Code tracing: See WBS W8 |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-3 | Code tracing: See WBS W8 |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-4 | Code tracing: See WBS W8 |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-5 | Code tracing: See WBS W8 |  |  | 林俊佑 | 2023-11-09 08:00 | Closed
W8-6 | Code tracing: See WBS W8 |  |  | 陳君翰 | 2023-11-09 08:00 | Closed
W8-7 | Complete weekly slides (code tracing) and homework/design |  |  | all | 2023-11-09 08:00 | Closed
W8-8 | Upload HW1 (jira) |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-9 | Upload HW2 (jira) |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-10 | Summarize Dependency Injection (jira) |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-11 | Create Gitlab group account |  |  | 林俊佑 | 2023-11-09 08:00 | Suspend
W8-12 | Exam place and all related issues |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W7-1 | Code tracing: See WBS W7 |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W7-2 | Code tracing: See WBS W7 |  |  | 洪世彬 | 2023-11-02 08:00 | Closed
W7-3 | Code tracing: See WBS W7 |  |  | 劉玠均 | 2023-11-02 08:00 | Closed
W7-4 | Code tracing: See WBS W7 |  |  | 楊昕叡 | 2023-11-02 08:00 | Closed
W7-5 | Code tracing: See WBS W7 |  |  | 林俊佑 | 2023-11-02 08:00 | Closed
W7-6 | Code tracing: See WBS W7 |  |  | 陳君翰 | 2023-11-02 08:00 | Closed
W7-7 | Complete weekly slides (code tracing) |  |  | all | 2023-11-02 08:00 | Closed
W7-8 | Homework 0-2 (P83-P85) (jira) |  |  | all | 2023-11-01 20:00 | Closed
W7-9 | Complete inner class slide |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W6-1 | Code tracing: See WBS W6 |  |  | 許庭瑋 | 2023-10-26 08:00 | Closed
W6-2 | Code tracing: See WBS W6 |  |  | 洪世彬 | 2023-10-26 08:00 | Closed
W6-3 | Code tracing: See WBS W6 |  |  | 劉玠均 | 2023-10-26 08:00 | Closed
W6-4 | Code tracing: See WBS W6 |  |  | 楊昕叡 | 2023-10-26 08:00 | Closed
W6-5 | Code tracing: See WBS W6 |  |  | 林俊佑 | 2023-10-26 08:00 | Closed
W6-6 | Code tracing: See WBS W6 |  |  | 陳君翰 | 2023-10-26 08:00 | Closed
W6-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-26 08:00 | Closed
W6-8 | 在 JIRA 新增自己的 issues |  |  | all | 2023-10-26 08:00 | Closed
W5-1 | Code tracing: See WBS W5 |  |  | 許庭瑋 | 2023-10-19 08:00 | Closed
W5-2 | Code tracing: See WBS W5 |  |  | 洪世彬 | 2023-10-19 08:00 | Closed
W5-3 | Code tracing: See WBS W5 |  |  | 劉玠均 | 2023-10-19 08:00 | Closed
W5-4 | Code tracing: See WBS W5 |  |  | 楊昕叡 | 2023-10-19 08:00 | Closed
W5-5 | Code tracing: See WBS W5 |  |  | 林俊佑 | 2023-10-19 08:00 | Closed
W5-6 | Code tracing: See WBS W5 |  |  | 陳君翰 | 2023-10-19 08:00 | Closed
W5-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-19 08:00 | Closed
W4-1 | WBS: 列出到 W13 的時間規劃 |  |  | all | 2023-10-12 08:00 | Closed
W4-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 12:00 | Closed
W4-3 | Code tracing: AbstractFileResolvingResource.java, ClassPathResource.java, UrlResource.java, ResourceUtils.java |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed
W4-4 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-12 08:00 | Closed
W4-5 | Code tracing: ConvertingComparator<S, T>, DefaultConversionService, 8 default converters |  |  | 劉玠均 | 2023-10-12 08:00 | Closed
W4-6 | Code tracing: AnnotationsScanner.java, AttributeMethods.java |  |  | 楊昕叡 | 2023-10-12 08:00 | Closed
W4-7 | Code tracing: spring-core-cglib |  |  | 林俊佑 | 2023-10-12 08:00 | Closed
W4-8 | Code tracing: aot.generate |  |  | 陳君翰 | 2023-10-12 08:00 | Closed
W4-9 | Complete weekly slides (整合 HW4 & HW5 答案 & code tracing） |  |  | all | 2023-10-12 08:00 | Closed
W3-1 | 重新定 code tracing 分工: spring-core-core |  |  | all | 2023-09-28 | Closed
W3-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed | moved to next week
W3-3 | 依新分工調整 WBS (LOC, responsibility, effort) |  |  | all | 2023-10-03 19:00 | Closed
W3-4 | Survey issue tracking system |  |  | all | 2023-10-03 19:00 | Closed
W3-5 | 釐清 W4 presentation focus、progress report |  |  | 許庭瑋 | 2023-10-03 19:00 | Closed
W3-6 | 確定 spring-core-core others 細部分工 |  |  | 劉玠均、洪世彬 | 2023-09-29 | Closed
W3-7 | 確定 spring-core-aot, spring-core-cglib 細部分工 |  |  | 林俊佑、陳君翰 | 2023-10-03 | Closed
W3-8 | Code tracing: spring-core-io |  |  | 許庭瑋 | 2023-10-05 08:00 | Closed
W3-9 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-05 08:00 | Closed
W3-10 | Code tracing: W3 in WBS (i.e., spring-core converter/*.java, GenericConversionService.java) |  |  | 劉玠均 | 2023-10-05 08:00 | Closed
W3-11 | Code tracing:W3 in WBS |  |  | 楊昕叡 | 2023-10-05 08:00 | Closed
W3-12 | Code tracing: spring-core-cglib 內 proxy |  |  | 林俊佑 | 2023-10-05 08:00 | Closed
W3-13 | Code tracing: spring-core-cglib 內 proxy |  |  | 陳君翰 | 2023-10-05 08:00 | Closed
W3-14 | Complete JIRA slides |  |  | 林俊佑、洪世彬 | 2023-10-05 08:00 | Closed
W3-15 | Complete weekly slides |  |  | all | 2023-10-05 08:00 | Closed
W2-1 | Code tracing 分工 |  |  | All | 2023-09-24 | Closed
W2-2 | Complete week 2 slide |  |  | All | 2023-09-25 20:00 | Closed
W2-3 | 釐清 WBS 書寫方式 |  |  | 許庭瑋 | 2023-09-28 08:00 | Closed
W2-4 | 看spring-expression的code |  |  | 許庭瑋 | 2023-12-21 | Suspend | focus on Spring-Core
W2-5 | 看spring-core-aot….的code |  |  | 陳君翰 | 2023-12-21 | Suspend
W2-6 | 看spring-beans的code |  |  | 洪世彬 | 2023-12-21 | Suspend
W2-7 | 看spring-core-core-annotation …的code |  |  | 劉玠均 | 2023-12-21 | Suspend
W2-8 | 看spring-context的code |  |  | 楊昕叡 | 2023-12-21 | Suspend
W2-9 | 看spring-core-cglib, spring-core-asm的code |  |  | 林俊佑 | 2023-12-21 | Suspend
W1-1 | Survey Spring Boot |  |  | 許庭瑋 | 2023-09-19 | Closed
W1-2 | Survey Spring Cloud |  |  | 陳君翰 | 2023-09-19 | Closed
W1-3 | Survey Spring Framework - Core Container |  |  | 劉玠均 | 2023-09-19 | Closed
W1-4 | Survey Spring Framework - AOP |  |  | 楊昕叡 | 2023-09-19 | Closed
W1-5 | Survey Spring Framework - Data Access/Integration |  |  | 洪世彬 | 2023-09-19 | Closed
W1-6 | Survey Spring Framework - Web (MVC/Remoting) |  |  | 林俊佑 | 2023-09-19 | Closed
W1-7 | Summarize Spring components in the slide |  |  | All | 2023-09-20 20:00 | Closed
W1-8 | Complete AOP slide |  |  | 楊昕叡 | 2023-09-20 20:00 | Closed
W1-9 | Complete ORM / JDBC slide |  |  | 洪世彬 | 2023-09-20 20:00 | Closed

## 1128 (W11)
Group 2 Meeting Minutes
Date |  | 2023-11-28
Time |  | 19:00-20:00
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論本週作業、分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- Discuss code tracing issue & homework designs - Discuss thread pool and immutable object
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1njBxJ_jDVkAZh2cov9TVD5a_GlULJFXrXwTekVSXv0Y/edit?usp=sharing
WBS |  | WBS
Jira Board |  | https://leon1234858.atlassian.net/jira/software/projects/SPRING/boards/1
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note (not Closed?)
W11-1 | Code tracing: See WBS W11 |  |  | 許庭瑋 | 2023-11-30 08:00 | Closed
W11-2 | Code tracing: See WBS W11 |  |  | 洪世彬 | 2023-11-30 08:00 | Closed
W11-3 | Code tracing: See WBS W11 |  |  | 劉玠均 | 2023-11-30 08:00 | Closed
W11-4 | Code tracing: See WBS W11 |  |  | 楊昕叡 | 2023-11-30 08:00 | Closed
W11-5 | Code tracing: See WBS W11 |  |  | 林俊佑 | 2023-11-30 08:00 | Closed
W11-6 | Code tracing: See WBS W11 |  |  | 陳君翰 | 2023-11-30 08:00 | Closed
W11-7 | Complete weekly slides and homework/design |  |  | all | 2023-11-30 08:00 | Closed
W11-8 | Upload HW1-PrintOut (jira) |  |  | 林俊佑 | 2023-11-30 08:00 | Closed
W11-9 | Upload HW2-SchematicCaptureSystems (jira) |  |  | 劉玠均 | 2023-11-30 08:00 | Closed
W11-10 | Upload HW3-EmailHandler (jira) |  |  | 楊昕叡 | 2023-11-30 08:00 | Closed
W11-11 | Upload HW4-WindowFramework (jira) |  |  | 陳君翰 | 2023-11-30 08:00 | Closed
W11-12 | Summarize HW0-1: Thread Pool (jira) |  |  | 許庭瑋 | 2023-11-30 08:00 | Closed
W11-13 | Summarize HW0-2: ImmutableObject (jira) |  |  | 洪世彬 | 2023-11-30 08:00 | Closed
W10-1 | Code tracing: See WBS W10 |  |  | 許庭瑋 | 2023-11-23 08:00 | Closed
W10-2 | Code tracing: See WBS W10 |  |  | 洪世彬 | 2023-11-23 08:00 | Closed
W10-3 | Code tracing: See WBS W10 |  |  | 劉玠均 | 2023-11-23 08:00 | Closed
W10-4 | Code tracing: See WBS W10 |  |  | 楊昕叡 | 2023-11-23 08:00 | Closed
W10-5 | Code tracing: See WBS W10 |  |  | 林俊佑 | 2023-11-23 08:00 | Closed
W10-6 | Code tracing: See WBS W10 |  |  | 陳君翰 | 2023-11-23 08:00 | Closed
W10-7 | Complete weekly slides and homework/design |  |  | all | 2023-11-23 08:00 | Closed
W10-8 | Upload HW1 (jira) |  |  | 劉玠均 | 2023-11-21 19:00 | Closed
W10-9 | Upload HW2 (jira) |  |  | 林俊佑 | 2023-11-21 19:00 | Closed
W10-10 | Upload HW3 (jira) |  |  | 洪世彬 | 2023-11-21 19:00 | Closed
W10-11 | Summarize answer to "Can we add duplicate responsibilities? (8-1, p.20)" |  |  | 陳君翰 | 2023-11-21 19:00 | Closed
W9-1 | Code tracing: See WBS W9 |  |  | 許庭瑋 | 2023-11-16 08:00 | Closed
W9-2 | Code tracing: See WBS W9 |  |  | 洪世彬 | 2023-11-16 08:00 | Closed
W9-3 | Code tracing: See WBS W9 |  |  | 劉玠均 | 2023-11-16 08:00 | Closed
W9-4 | Code tracing: See WBS W9 |  |  | 楊昕叡 | 2023-11-16 08:00 | Closed
W9-5 | Code tracing: See WBS W9 |  |  | 林俊佑 | 2023-11-16 08:00 | Closed
W9-6 | Code tracing: See WBS W9 |  |  | 陳君翰 | 2023-11-16 08:00 | Closed
W9-7 | Complete weekly slides |  |  | all | 2023-11-16 08:00 | Closed
W8-1 | Code tracing: See WBS W8 |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W8-2 | Code tracing: See WBS W8 |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-3 | Code tracing: See WBS W8 |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-4 | Code tracing: See WBS W8 |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-5 | Code tracing: See WBS W8 |  |  | 林俊佑 | 2023-11-09 08:00 | Closed
W8-6 | Code tracing: See WBS W8 |  |  | 陳君翰 | 2023-11-09 08:00 | Closed
W8-7 | Complete weekly slides (code tracing) and homework/design |  |  | all | 2023-11-09 08:00 | Closed
W8-8 | Upload HW1 (jira) |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-9 | Upload HW2 (jira) |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-10 | Summarize Dependency Injection (jira) |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-11 | Create Gitlab group account |  |  | 林俊佑 | 2023-11-09 08:00 | Suspend
W8-12 | Exam place and all related issues |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W7-1 | Code tracing: See WBS W7 |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W7-2 | Code tracing: See WBS W7 |  |  | 洪世彬 | 2023-11-02 08:00 | Closed
W7-3 | Code tracing: See WBS W7 |  |  | 劉玠均 | 2023-11-02 08:00 | Closed
W7-4 | Code tracing: See WBS W7 |  |  | 楊昕叡 | 2023-11-02 08:00 | Closed
W7-5 | Code tracing: See WBS W7 |  |  | 林俊佑 | 2023-11-02 08:00 | Closed
W7-6 | Code tracing: See WBS W7 |  |  | 陳君翰 | 2023-11-02 08:00 | Closed
W7-7 | Complete weekly slides (code tracing) |  |  | all | 2023-11-02 08:00 | Closed
W7-8 | Homework 0-2 (P83-P85) (jira) |  |  | all | 2023-11-01 20:00 | Closed
W7-9 | Complete inner class slide |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W6-1 | Code tracing: See WBS W6 |  |  | 許庭瑋 | 2023-10-26 08:00 | Closed
W6-2 | Code tracing: See WBS W6 |  |  | 洪世彬 | 2023-10-26 08:00 | Closed
W6-3 | Code tracing: See WBS W6 |  |  | 劉玠均 | 2023-10-26 08:00 | Closed
W6-4 | Code tracing: See WBS W6 |  |  | 楊昕叡 | 2023-10-26 08:00 | Closed
W6-5 | Code tracing: See WBS W6 |  |  | 林俊佑 | 2023-10-26 08:00 | Closed
W6-6 | Code tracing: See WBS W6 |  |  | 陳君翰 | 2023-10-26 08:00 | Closed
W6-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-26 08:00 | Closed
W6-8 | 在 JIRA 新增自己的 issues |  |  | all | 2023-10-26 08:00 | Closed
W5-1 | Code tracing: See WBS W5 |  |  | 許庭瑋 | 2023-10-19 08:00 | Closed
W5-2 | Code tracing: See WBS W5 |  |  | 洪世彬 | 2023-10-19 08:00 | Closed
W5-3 | Code tracing: See WBS W5 |  |  | 劉玠均 | 2023-10-19 08:00 | Closed
W5-4 | Code tracing: See WBS W5 |  |  | 楊昕叡 | 2023-10-19 08:00 | Closed
W5-5 | Code tracing: See WBS W5 |  |  | 林俊佑 | 2023-10-19 08:00 | Closed
W5-6 | Code tracing: See WBS W5 |  |  | 陳君翰 | 2023-10-19 08:00 | Closed
W5-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-19 08:00 | Closed
W4-1 | WBS: 列出到 W13 的時間規劃 |  |  | all | 2023-10-12 08:00 | Closed
W4-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 12:00 | Closed
W4-3 | Code tracing: AbstractFileResolvingResource.java, ClassPathResource.java, UrlResource.java, ResourceUtils.java |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed
W4-4 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-12 08:00 | Closed
W4-5 | Code tracing: ConvertingComparator<S, T>, DefaultConversionService, 8 default converters |  |  | 劉玠均 | 2023-10-12 08:00 | Closed
W4-6 | Code tracing: AnnotationsScanner.java, AttributeMethods.java |  |  | 楊昕叡 | 2023-10-12 08:00 | Closed
W4-7 | Code tracing: spring-core-cglib |  |  | 林俊佑 | 2023-10-12 08:00 | Closed
W4-8 | Code tracing: aot.generate |  |  | 陳君翰 | 2023-10-12 08:00 | Closed
W4-9 | Complete weekly slides (整合 HW4 & HW5 答案 & code tracing） |  |  | all | 2023-10-12 08:00 | Closed
W3-1 | 重新定 code tracing 分工: spring-core-core |  |  | all | 2023-09-28 | Closed
W3-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed | moved to next week
W3-3 | 依新分工調整 WBS (LOC, responsibility, effort) |  |  | all | 2023-10-03 19:00 | Closed
W3-4 | Survey issue tracking system |  |  | all | 2023-10-03 19:00 | Closed
W3-5 | 釐清 W4 presentation focus、progress report |  |  | 許庭瑋 | 2023-10-03 19:00 | Closed
W3-6 | 確定 spring-core-core others 細部分工 |  |  | 劉玠均、洪世彬 | 2023-09-29 | Closed
W3-7 | 確定 spring-core-aot, spring-core-cglib 細部分工 |  |  | 林俊佑、陳君翰 | 2023-10-03 | Closed
W3-8 | Code tracing: spring-core-io |  |  | 許庭瑋 | 2023-10-05 08:00 | Closed
W3-9 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-05 08:00 | Closed
W3-10 | Code tracing: W3 in WBS (i.e., spring-core converter/*.java, GenericConversionService.java) |  |  | 劉玠均 | 2023-10-05 08:00 | Closed
W3-11 | Code tracing:W3 in WBS |  |  | 楊昕叡 | 2023-10-05 08:00 | Closed
W3-12 | Code tracing: spring-core-cglib 內 proxy |  |  | 林俊佑 | 2023-10-05 08:00 | Closed
W3-13 | Code tracing: spring-core-cglib 內 proxy |  |  | 陳君翰 | 2023-10-05 08:00 | Closed
W3-14 | Complete JIRA slides |  |  | 林俊佑、洪世彬 | 2023-10-05 08:00 | Closed
W3-15 | Complete weekly slides |  |  | all | 2023-10-05 08:00 | Closed
W2-1 | Code tracing 分工 |  |  | All | 2023-09-24 | Closed
W2-2 | Complete week 2 slide |  |  | All | 2023-09-25 20:00 | Closed
W2-3 | 釐清 WBS 書寫方式 |  |  | 許庭瑋 | 2023-09-28 08:00 | Closed
W2-4 | 看spring-expression的code |  |  | 許庭瑋 | 2023-12-21 | Suspend | focus on Spring-Core
W2-5 | 看spring-core-aot….的code |  |  | 陳君翰 | 2023-12-21 | Suspend
W2-6 | 看spring-beans的code |  |  | 洪世彬 | 2023-12-21 | Suspend
W2-7 | 看spring-core-core-annotation …的code |  |  | 劉玠均 | 2023-12-21 | Suspend
W2-8 | 看spring-context的code |  |  | 楊昕叡 | 2023-12-21 | Suspend
W2-9 | 看spring-core-cglib, spring-core-asm的code |  |  | 林俊佑 | 2023-12-21 | Suspend
W1-1 | Survey Spring Boot |  |  | 許庭瑋 | 2023-09-19 | Closed
W1-2 | Survey Spring Cloud |  |  | 陳君翰 | 2023-09-19 | Closed
W1-3 | Survey Spring Framework - Core Container |  |  | 劉玠均 | 2023-09-19 | Closed
W1-4 | Survey Spring Framework - AOP |  |  | 楊昕叡 | 2023-09-19 | Closed
W1-5 | Survey Spring Framework - Data Access/Integration |  |  | 洪世彬 | 2023-09-19 | Closed
W1-6 | Survey Spring Framework - Web (MVC/Remoting) |  |  | 林俊佑 | 2023-09-19 | Closed
W1-7 | Summarize Spring components in the slide |  |  | All | 2023-09-20 20:00 | Closed
W1-8 | Complete AOP slide |  |  | 楊昕叡 | 2023-09-20 20:00 | Closed
W1-9 | Complete ORM / JDBC slide |  |  | 洪世彬 | 2023-09-20 20:00 | Closed

## 1120 (W10)
Group 2 Meeting Minutes
Date |  | 2023-11-20
Time |  | 19:00-20:20
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論本週作業、分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- Discuss code tracing issue & homework designs - Discuss "Can we add duplicate responsibilities?" (8-1) P20
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1Gsnt9hwsbrSxwqNPqVCMNEIrmkaqVPqeURrFTN6mAMU/edit?usp=sharing
WBS |  | WBS
Jira Board |  | https://leon1234858.atlassian.net/jira/software/projects/SPRING/boards/1
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note (not Closed?)
W10-1 | Code tracing: See WBS W10 |  |  | 許庭瑋 | 2023-11-23 08:00 | Closed
W10-2 | Code tracing: See WBS W10 |  |  | 洪世彬 | 2023-11-23 08:00 | Closed
W10-3 | Code tracing: See WBS W10 |  |  | 劉玠均 | 2023-11-23 08:00 | Closed
W10-4 | Code tracing: See WBS W10 |  |  | 楊昕叡 | 2023-11-23 08:00 | Closed
W10-5 | Code tracing: See WBS W10 |  |  | 林俊佑 | 2023-11-23 08:00 | Closed
W10-6 | Code tracing: See WBS W10 |  |  | 陳君翰 | 2023-11-23 08:00 | Closed
W10-7 | Complete weekly slides and homework/design |  |  | all | 2023-11-23 08:00 | Closed
W10-8 | Upload HW1 (jira) |  |  | 劉玠均 | 2023-11-21 19:00 | Closed
W10-9 | Upload HW2 (jira) |  |  | 林俊佑 | 2023-11-21 19:00 | Closed
W10-10 | Upload HW3 (jira) |  |  | 洪世彬 | 2023-11-21 19:00 | Closed
W10-11 | Summarize answer to "Can we add duplicate responsibilities? (8-1, p.20)" |  |  | 陳君翰 | 2023-11-21 19:00 | Closed
W9-1 | Code tracing: See WBS W9 |  |  | 許庭瑋 | 2023-11-16 08:00 | Closed
W9-2 | Code tracing: See WBS W9 |  |  | 洪世彬 | 2023-11-16 08:00 | Closed
W9-3 | Code tracing: See WBS W9 |  |  | 劉玠均 | 2023-11-16 08:00 | Closed
W9-4 | Code tracing: See WBS W9 |  |  | 楊昕叡 | 2023-11-16 08:00 | Closed
W9-5 | Code tracing: See WBS W9 |  |  | 林俊佑 | 2023-11-16 08:00 | Closed
W9-6 | Code tracing: See WBS W9 |  |  | 陳君翰 | 2023-11-16 08:00 | Closed
W9-7 | Complete weekly slides |  |  | all | 2023-11-16 08:00 | Closed
W8-1 | Code tracing: See WBS W8 |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W8-2 | Code tracing: See WBS W8 |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-3 | Code tracing: See WBS W8 |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-4 | Code tracing: See WBS W8 |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-5 | Code tracing: See WBS W8 |  |  | 林俊佑 | 2023-11-09 08:00 | Closed
W8-6 | Code tracing: See WBS W8 |  |  | 陳君翰 | 2023-11-09 08:00 | Closed
W8-7 | Complete weekly slides (code tracing) and homework/design |  |  | all | 2023-11-09 08:00 | Closed
W8-8 | Upload HW1 (jira) |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-9 | Upload HW2 (jira) |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-10 | Summarize Dependency Injection (jira) |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-11 | Create Gitlab group account |  |  | 林俊佑 | 2023-11-09 08:00 | Suspend
W8-12 | Exam place and all related issues |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W7-1 | Code tracing: See WBS W7 |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W7-2 | Code tracing: See WBS W7 |  |  | 洪世彬 | 2023-11-02 08:00 | Closed
W7-3 | Code tracing: See WBS W7 |  |  | 劉玠均 | 2023-11-02 08:00 | Closed
W7-4 | Code tracing: See WBS W7 |  |  | 楊昕叡 | 2023-11-02 08:00 | Closed
W7-5 | Code tracing: See WBS W7 |  |  | 林俊佑 | 2023-11-02 08:00 | Closed
W7-6 | Code tracing: See WBS W7 |  |  | 陳君翰 | 2023-11-02 08:00 | Closed
W7-7 | Complete weekly slides (code tracing) |  |  | all | 2023-11-02 08:00 | Closed
W7-8 | Homework 0-2 (P83-P85) (jira) |  |  | all | 2023-11-01 20:00 | Closed
W7-9 | Complete inner class slide |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W6-1 | Code tracing: See WBS W6 |  |  | 許庭瑋 | 2023-10-26 08:00 | Closed
W6-2 | Code tracing: See WBS W6 |  |  | 洪世彬 | 2023-10-26 08:00 | Closed
W6-3 | Code tracing: See WBS W6 |  |  | 劉玠均 | 2023-10-26 08:00 | Closed
W6-4 | Code tracing: See WBS W6 |  |  | 楊昕叡 | 2023-10-26 08:00 | Closed
W6-5 | Code tracing: See WBS W6 |  |  | 林俊佑 | 2023-10-26 08:00 | Closed
W6-6 | Code tracing: See WBS W6 |  |  | 陳君翰 | 2023-10-26 08:00 | Closed
W6-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-26 08:00 | Closed
W6-8 | 在 JIRA 新增自己的 issues |  |  | all | 2023-10-26 08:00 | Closed
W5-1 | Code tracing: See WBS W5 |  |  | 許庭瑋 | 2023-10-19 08:00 | Closed
W5-2 | Code tracing: See WBS W5 |  |  | 洪世彬 | 2023-10-19 08:00 | Closed
W5-3 | Code tracing: See WBS W5 |  |  | 劉玠均 | 2023-10-19 08:00 | Closed
W5-4 | Code tracing: See WBS W5 |  |  | 楊昕叡 | 2023-10-19 08:00 | Closed
W5-5 | Code tracing: See WBS W5 |  |  | 林俊佑 | 2023-10-19 08:00 | Closed
W5-6 | Code tracing: See WBS W5 |  |  | 陳君翰 | 2023-10-19 08:00 | Closed
W5-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-19 08:00 | Closed
W4-1 | WBS: 列出到 W13 的時間規劃 |  |  | all | 2023-10-12 08:00 | Closed
W4-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 12:00 | Closed
W4-3 | Code tracing: AbstractFileResolvingResource.java, ClassPathResource.java, UrlResource.java, ResourceUtils.java |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed
W4-4 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-12 08:00 | Closed
W4-5 | Code tracing: ConvertingComparator<S, T>, DefaultConversionService, 8 default converters |  |  | 劉玠均 | 2023-10-12 08:00 | Closed
W4-6 | Code tracing: AnnotationsScanner.java, AttributeMethods.java |  |  | 楊昕叡 | 2023-10-12 08:00 | Closed
W4-7 | Code tracing: spring-core-cglib |  |  | 林俊佑 | 2023-10-12 08:00 | Closed
W4-8 | Code tracing: aot.generate |  |  | 陳君翰 | 2023-10-12 08:00 | Closed
W4-9 | Complete weekly slides (整合 HW4 & HW5 答案 & code tracing） |  |  | all | 2023-10-12 08:00 | Closed
W3-1 | 重新定 code tracing 分工: spring-core-core |  |  | all | 2023-09-28 | Closed
W3-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed | moved to next week
W3-3 | 依新分工調整 WBS (LOC, responsibility, effort) |  |  | all | 2023-10-03 19:00 | Closed
W3-4 | Survey issue tracking system |  |  | all | 2023-10-03 19:00 | Closed
W3-5 | 釐清 W4 presentation focus、progress report |  |  | 許庭瑋 | 2023-10-03 19:00 | Closed
W3-6 | 確定 spring-core-core others 細部分工 |  |  | 劉玠均、洪世彬 | 2023-09-29 | Closed
W3-7 | 確定 spring-core-aot, spring-core-cglib 細部分工 |  |  | 林俊佑、陳君翰 | 2023-10-03 | Closed
W3-8 | Code tracing: spring-core-io |  |  | 許庭瑋 | 2023-10-05 08:00 | Closed
W3-9 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-05 08:00 | Closed
W3-10 | Code tracing: W3 in WBS (i.e., spring-core converter/*.java, GenericConversionService.java) |  |  | 劉玠均 | 2023-10-05 08:00 | Closed
W3-11 | Code tracing:W3 in WBS |  |  | 楊昕叡 | 2023-10-05 08:00 | Closed
W3-12 | Code tracing: spring-core-cglib 內 proxy |  |  | 林俊佑 | 2023-10-05 08:00 | Closed
W3-13 | Code tracing: spring-core-cglib 內 proxy |  |  | 陳君翰 | 2023-10-05 08:00 | Closed
W3-14 | Complete JIRA slides |  |  | 林俊佑、洪世彬 | 2023-10-05 08:00 | Closed
W3-15 | Complete weekly slides |  |  | all | 2023-10-05 08:00 | Closed
W2-1 | Code tracing 分工 |  |  | All | 2023-09-24 | Closed
W2-2 | Complete week 2 slide |  |  | All | 2023-09-25 20:00 | Closed
W2-3 | 釐清 WBS 書寫方式 |  |  | 許庭瑋 | 2023-09-28 08:00 | Closed
W2-4 | 看spring-expression的code |  |  | 許庭瑋 | 2023-12-21 | Suspend | focus on Spring-Core
W2-5 | 看spring-core-aot….的code |  |  | 陳君翰 | 2023-12-21 | Suspend
W2-6 | 看spring-beans的code |  |  | 洪世彬 | 2023-12-21 | Suspend
W2-7 | 看spring-core-core-annotation …的code |  |  | 劉玠均 | 2023-12-21 | Suspend
W2-8 | 看spring-context的code |  |  | 楊昕叡 | 2023-12-21 | Suspend
W2-9 | 看spring-core-cglib, spring-core-asm的code |  |  | 林俊佑 | 2023-12-21 | Suspend
W1-1 | Survey Spring Boot |  |  | 許庭瑋 | 2023-09-19 | Closed
W1-2 | Survey Spring Cloud |  |  | 陳君翰 | 2023-09-19 | Closed
W1-3 | Survey Spring Framework - Core Container |  |  | 劉玠均 | 2023-09-19 | Closed
W1-4 | Survey Spring Framework - AOP |  |  | 楊昕叡 | 2023-09-19 | Closed
W1-5 | Survey Spring Framework - Data Access/Integration |  |  | 洪世彬 | 2023-09-19 | Closed
W1-6 | Survey Spring Framework - Web (MVC/Remoting) |  |  | 林俊佑 | 2023-09-19 | Closed
W1-7 | Summarize Spring components in the slide |  |  | All | 2023-09-20 20:00 | Closed
W1-8 | Complete AOP slide |  |  | 楊昕叡 | 2023-09-20 20:00 | Closed
W1-9 | Complete ORM / JDBC slide |  |  | 洪世彬 | 2023-09-20 20:00 | Closed

## 1114 (W9)
Group 2 Meeting Minutes
Date |  | 2023-11-14
Time |  | 19:00-19:35
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- Discuss code tracing issue - Discuss UML: nested classifier in UML 1.4 and UML 2.x (reference: https://stackoverflow.com/questions/27797531/how-to-represent-the-nested-class-of-c-in-uml , https://www.uml-diagrams.org/nested-classifier.html)
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1AJ8_icuteJCMxEtBWLqkePtqRdVVgrvtwccPfNujFtU/edit?usp=sharing
WBS |  | WBS
Jira Board |  | https://leon1234858.atlassian.net/jira/software/projects/SPRING/boards/1
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note (not Closed?)
W9-1 | Code tracing: See WBS W9 |  |  | 許庭瑋 | 2023-11-16 08:00 | Closed
W9-2 | Code tracing: See WBS W9 |  |  | 洪世彬 | 2023-11-16 08:00 | Closed
W9-3 | Code tracing: See WBS W9 |  |  | 劉玠均 | 2023-11-16 08:00 | Closed
W9-4 | Code tracing: See WBS W9 |  |  | 楊昕叡 | 2023-11-16 08:00 | Closed
W9-5 | Code tracing: See WBS W9 |  |  | 林俊佑 | 2023-11-16 08:00 | Closed
W9-6 | Code tracing: See WBS W9 |  |  | 陳君翰 | 2023-11-16 08:00 | Closed
W9-7 | Complete weekly slides |  |  | all | 2023-11-16 08:00 | Closed
W8-1 | Code tracing: See WBS W8 |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W8-2 | Code tracing: See WBS W8 |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-3 | Code tracing: See WBS W8 |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-4 | Code tracing: See WBS W8 |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-5 | Code tracing: See WBS W8 |  |  | 林俊佑 | 2023-11-09 08:00 | Closed
W8-6 | Code tracing: See WBS W8 |  |  | 陳君翰 | 2023-11-09 08:00 | Closed
W8-7 | Complete weekly slides (code tracing) and homework/design |  |  | all | 2023-11-09 08:00 | Closed
W8-8 | Upload HW1 (jira) |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-9 | Upload HW2 (jira) |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-10 | Summarize Dependency Injection (jira) |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-11 | Create Gitlab group account |  |  | 林俊佑 | 2023-11-09 08:00 | Suspend
W8-12 | Exam place and all related issues |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W7-1 | Code tracing: See WBS W7 |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W7-2 | Code tracing: See WBS W7 |  |  | 洪世彬 | 2023-11-02 08:00 | Closed
W7-3 | Code tracing: See WBS W7 |  |  | 劉玠均 | 2023-11-02 08:00 | Closed
W7-4 | Code tracing: See WBS W7 |  |  | 楊昕叡 | 2023-11-02 08:00 | Closed
W7-5 | Code tracing: See WBS W7 |  |  | 林俊佑 | 2023-11-02 08:00 | Closed
W7-6 | Code tracing: See WBS W7 |  |  | 陳君翰 | 2023-11-02 08:00 | Closed
W7-7 | Complete weekly slides (code tracing) |  |  | all | 2023-11-02 08:00 | Closed
W7-8 | Homework 0-2 (P83-P85) (jira) |  |  | all | 2023-11-01 20:00 | Closed
W7-9 | Complete inner class slide |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W6-1 | Code tracing: See WBS W6 |  |  | 許庭瑋 | 2023-10-26 08:00 | Closed
W6-2 | Code tracing: See WBS W6 |  |  | 洪世彬 | 2023-10-26 08:00 | Closed
W6-3 | Code tracing: See WBS W6 |  |  | 劉玠均 | 2023-10-26 08:00 | Closed
W6-4 | Code tracing: See WBS W6 |  |  | 楊昕叡 | 2023-10-26 08:00 | Closed
W6-5 | Code tracing: See WBS W6 |  |  | 林俊佑 | 2023-10-26 08:00 | Closed
W6-6 | Code tracing: See WBS W6 |  |  | 陳君翰 | 2023-10-26 08:00 | Closed
W6-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-26 08:00 | Closed
W6-8 | 在 JIRA 新增自己的 issues |  |  | all | 2023-10-26 08:00 | Closed
W5-1 | Code tracing: See WBS W5 |  |  | 許庭瑋 | 2023-10-19 08:00 | Closed
W5-2 | Code tracing: See WBS W5 |  |  | 洪世彬 | 2023-10-19 08:00 | Closed
W5-3 | Code tracing: See WBS W5 |  |  | 劉玠均 | 2023-10-19 08:00 | Closed
W5-4 | Code tracing: See WBS W5 |  |  | 楊昕叡 | 2023-10-19 08:00 | Closed
W5-5 | Code tracing: See WBS W5 |  |  | 林俊佑 | 2023-10-19 08:00 | Closed
W5-6 | Code tracing: See WBS W5 |  |  | 陳君翰 | 2023-10-19 08:00 | Closed
W5-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-19 08:00 | Closed
W4-1 | WBS: 列出到 W13 的時間規劃 |  |  | all | 2023-10-12 08:00 | Closed
W4-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 12:00 | Closed
W4-3 | Code tracing: AbstractFileResolvingResource.java, ClassPathResource.java, UrlResource.java, ResourceUtils.java |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed
W4-4 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-12 08:00 | Closed
W4-5 | Code tracing: ConvertingComparator<S, T>, DefaultConversionService, 8 default converters |  |  | 劉玠均 | 2023-10-12 08:00 | Closed
W4-6 | Code tracing: AnnotationsScanner.java, AttributeMethods.java |  |  | 楊昕叡 | 2023-10-12 08:00 | Closed
W4-7 | Code tracing: spring-core-cglib |  |  | 林俊佑 | 2023-10-12 08:00 | Closed
W4-8 | Code tracing: aot.generate |  |  | 陳君翰 | 2023-10-12 08:00 | Closed
W4-9 | Complete weekly slides (整合 HW4 & HW5 答案 & code tracing） |  |  | all | 2023-10-12 08:00 | Closed
W3-1 | 重新定 code tracing 分工: spring-core-core |  |  | all | 2023-09-28 | Closed
W3-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed | moved to next week
W3-3 | 依新分工調整 WBS (LOC, responsibility, effort) |  |  | all | 2023-10-03 19:00 | Closed
W3-4 | Survey issue tracking system |  |  | all | 2023-10-03 19:00 | Closed
W3-5 | 釐清 W4 presentation focus、progress report |  |  | 許庭瑋 | 2023-10-03 19:00 | Closed
W3-6 | 確定 spring-core-core others 細部分工 |  |  | 劉玠均、洪世彬 | 2023-09-29 | Closed
W3-7 | 確定 spring-core-aot, spring-core-cglib 細部分工 |  |  | 林俊佑、陳君翰 | 2023-10-03 | Closed
W3-8 | Code tracing: spring-core-io |  |  | 許庭瑋 | 2023-10-05 08:00 | Closed
W3-9 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-05 08:00 | Closed
W3-10 | Code tracing: W3 in WBS (i.e., spring-core converter/*.java, GenericConversionService.java) |  |  | 劉玠均 | 2023-10-05 08:00 | Closed
W3-11 | Code tracing:W3 in WBS |  |  | 楊昕叡 | 2023-10-05 08:00 | Closed
W3-12 | Code tracing: spring-core-cglib 內 proxy |  |  | 林俊佑 | 2023-10-05 08:00 | Closed
W3-13 | Code tracing: spring-core-cglib 內 proxy |  |  | 陳君翰 | 2023-10-05 08:00 | Closed
W3-14 | Complete JIRA slides |  |  | 林俊佑、洪世彬 | 2023-10-05 08:00 | Closed
W3-15 | Complete weekly slides |  |  | all | 2023-10-05 08:00 | Closed
W2-1 | Code tracing 分工 |  |  | All | 2023-09-24 | Closed
W2-2 | Complete week 2 slide |  |  | All | 2023-09-25 20:00 | Closed
W2-3 | 釐清 WBS 書寫方式 |  |  | 許庭瑋 | 2023-09-28 08:00 | Closed
W2-4 | 看spring-expression的code |  |  | 許庭瑋 | 2023-12-21 | Suspend | focus on Spring-Core
W2-5 | 看spring-core-aot….的code |  |  | 陳君翰 | 2023-12-21 | Suspend
W2-6 | 看spring-beans的code |  |  | 洪世彬 | 2023-12-21 | Suspend
W2-7 | 看spring-core-core-annotation …的code |  |  | 劉玠均 | 2023-12-21 | Suspend
W2-8 | 看spring-context的code |  |  | 楊昕叡 | 2023-12-21 | Suspend
W2-9 | 看spring-core-cglib, spring-core-asm的code |  |  | 林俊佑 | 2023-12-21 | Suspend
W1-1 | Survey Spring Boot |  |  | 許庭瑋 | 2023-09-19 | Closed
W1-2 | Survey Spring Cloud |  |  | 陳君翰 | 2023-09-19 | Closed
W1-3 | Survey Spring Framework - Core Container |  |  | 劉玠均 | 2023-09-19 | Closed
W1-4 | Survey Spring Framework - AOP |  |  | 楊昕叡 | 2023-09-19 | Closed
W1-5 | Survey Spring Framework - Data Access/Integration |  |  | 洪世彬 | 2023-09-19 | Closed
W1-6 | Survey Spring Framework - Web (MVC/Remoting) |  |  | 林俊佑 | 2023-09-19 | Closed
W1-7 | Summarize Spring components in the slide |  |  | All | 2023-09-20 20:00 | Closed
W1-8 | Complete AOP slide |  |  | 楊昕叡 | 2023-09-20 20:00 | Closed
W1-9 | Complete ORM / JDBC slide |  |  | 洪世彬 | 2023-09-20 20:00 | Closed

## 1107 (W8)
Group 2 Meeting Minutes
Date |  | 2023-11-07
Time |  | 19:00-20:30
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論本週作業、上課提到的 Design Patterns (e.g., DI, strategy, observer ...)，分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- Discuss our homework designs and find the best answer - Discuss Dependency Injection (different types and use cases) - Code tracing issue
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1-HW_kkoCsdvJBCgAXMKfNgl5C2N3GFXRxobmCrnBvO4/edit?usp=sharing
WBS |  | WBS
Jira Board |  | https://leon1234858.atlassian.net/jira/software/projects/SPRING/boards/1
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status | Note (not Closed?)
W8-1 | Code tracing: See WBS W8 |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W8-2 | Code tracing: See WBS W8 |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-3 | Code tracing: See WBS W8 |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-4 | Code tracing: See WBS W8 |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-5 | Code tracing: See WBS W8 |  |  | 林俊佑 | 2023-11-09 08:00 | Closed
W8-6 | Code tracing: See WBS W8 |  |  | 陳君翰 | 2023-11-09 08:00 | Closed
W8-7 | Complete weekly slides (code tracing) and homework/design |  |  | all | 2023-11-09 08:00 | Closed
W8-8 | Upload HW1 (jira) |  |  | 洪世彬 | 2023-11-09 08:00 | Closed
W8-9 | Upload HW2 (jira) |  |  | 劉玠均 | 2023-11-09 08:00 | Closed
W8-10 | Summarize Dependency Injection (jira) |  |  | 楊昕叡 | 2023-11-09 08:00 | Closed
W8-11 | Create Gitlab group account |  |  | 林俊佑 | 2023-11-09 08:00 | Suspend
W8-12 | Exam place and all related issues |  |  | 許庭瑋 | 2023-11-09 08:00 | Closed
W7-1 | Code tracing: See WBS W7 |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W7-2 | Code tracing: See WBS W7 |  |  | 洪世彬 | 2023-11-02 08:00 | Closed
W7-3 | Code tracing: See WBS W7 |  |  | 劉玠均 | 2023-11-02 08:00 | Closed
W7-4 | Code tracing: See WBS W7 |  |  | 楊昕叡 | 2023-11-02 08:00 | Closed
W7-5 | Code tracing: See WBS W7 |  |  | 林俊佑 | 2023-11-02 08:00 | Closed
W7-6 | Code tracing: See WBS W7 |  |  | 陳君翰 | 2023-11-02 08:00 | Closed
W7-7 | Complete weekly slides (code tracing) |  |  | all | 2023-11-02 08:00 | Closed
W7-8 | Homework 0-2 (P83-P85) (jira) |  |  | all | 2023-11-01 20:00 | Closed
W7-9 | Complete inner class slide |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
W6-1 | Code tracing: See WBS W6 |  |  | 許庭瑋 | 2023-10-26 08:00 | Closed
W6-2 | Code tracing: See WBS W6 |  |  | 洪世彬 | 2023-10-26 08:00 | Closed
W6-3 | Code tracing: See WBS W6 |  |  | 劉玠均 | 2023-10-26 08:00 | Closed
W6-4 | Code tracing: See WBS W6 |  |  | 楊昕叡 | 2023-10-26 08:00 | Closed
W6-5 | Code tracing: See WBS W6 |  |  | 林俊佑 | 2023-10-26 08:00 | Closed
W6-6 | Code tracing: See WBS W6 |  |  | 陳君翰 | 2023-10-26 08:00 | Closed
W6-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-26 08:00 | Closed
W6-8 | 在 JIRA 新增自己的 issues |  |  | all | 2023-10-26 08:00 | Closed
W5-1 | Code tracing: See WBS W5 |  |  | 許庭瑋 | 2023-10-19 08:00 | Closed
W5-2 | Code tracing: See WBS W5 |  |  | 洪世彬 | 2023-10-19 08:00 | Closed
W5-3 | Code tracing: See WBS W5 |  |  | 劉玠均 | 2023-10-19 08:00 | Closed
W5-4 | Code tracing: See WBS W5 |  |  | 楊昕叡 | 2023-10-19 08:00 | Closed
W5-5 | Code tracing: See WBS W5 |  |  | 林俊佑 | 2023-10-19 08:00 | Closed
W5-6 | Code tracing: See WBS W5 |  |  | 陳君翰 | 2023-10-19 08:00 | Closed
W5-7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-19 08:00 | Closed
W4-1 | WBS: 列出到 W13 的時間規劃 |  |  | all | 2023-10-12 08:00 | Closed
W4-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 12:00 | Closed
W4-3 | Code tracing: AbstractFileResolvingResource.java, ClassPathResource.java, UrlResource.java, ResourceUtils.java |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed
W4-4 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-12 08:00 | Closed
W4-5 | Code tracing: ConvertingComparator<S, T>, DefaultConversionService, 8 default converters |  |  | 劉玠均 | 2023-10-12 08:00 | Closed
W4-6 | Code tracing: AnnotationsScanner.java, AttributeMethods.java |  |  | 楊昕叡 | 2023-10-12 08:00 | Closed
W4-7 | Code tracing: spring-core-cglib |  |  | 林俊佑 | 2023-10-12 08:00 | Closed
W4-8 | Code tracing: aot.generate |  |  | 陳君翰 | 2023-10-12 08:00 | Closed
W4-9 | Complete weekly slides (整合 HW4 & HW5 答案 & code tracing） |  |  | all | 2023-10-12 08:00 | Closed
W3-1 | 重新定 code tracing 分工: spring-core-core |  |  | all | 2023-09-28 | Closed
W3-2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed | moved to next week
W3-3 | 依新分工調整 WBS (LOC, responsibility, effort) |  |  | all | 2023-10-03 19:00 | Closed
W3-4 | Survey issue tracking system |  |  | all | 2023-10-03 19:00 | Closed
W3-5 | 釐清 W4 presentation focus、progress report |  |  | 許庭瑋 | 2023-10-03 19:00 | Closed
W3-6 | 確定 spring-core-core others 細部分工 |  |  | 劉玠均、洪世彬 | 2023-09-29 | Closed
W3-7 | 確定 spring-core-aot, spring-core-cglib 細部分工 |  |  | 林俊佑、陳君翰 | 2023-10-03 | Closed
W3-8 | Code tracing: spring-core-io |  |  | 許庭瑋 | 2023-10-05 08:00 | Closed
W3-9 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-05 08:00 | Closed
W3-10 | Code tracing: W3 in WBS (i.e., spring-core converter/*.java, GenericConversionService.java) |  |  | 劉玠均 | 2023-10-05 08:00 | Closed
W3-11 | Code tracing:W3 in WBS |  |  | 楊昕叡 | 2023-10-05 08:00 | Closed
W3-12 | Code tracing: spring-core-cglib 內 proxy |  |  | 林俊佑 | 2023-10-05 08:00 | Closed
W3-13 | Code tracing: spring-core-cglib 內 proxy |  |  | 陳君翰 | 2023-10-05 08:00 | Closed
W3-14 | Complete JIRA slides |  |  | 林俊佑、洪世彬 | 2023-10-05 08:00 | Closed
W3-15 | Complete weekly slides |  |  | all | 2023-10-05 08:00 | Closed
W2-1 | Code tracing 分工 |  |  | All | 2023-09-24 | Closed
W2-2 | Complete week 2 slide |  |  | All | 2023-09-25 20:00 | Closed
W2-3 | 釐清 WBS 書寫方式 |  |  | 許庭瑋 | 2023-09-28 08:00 | Closed
W2-4 | 看spring-expression的code |  |  | 許庭瑋 | 2023-12-21 | Suspend | focus on Spring-Core
W2-5 | 看spring-core-aot….的code |  |  | 陳君翰 | 2023-12-21 | Suspend
W2-6 | 看spring-beans的code |  |  | 洪世彬 | 2023-12-21 | Suspend
W2-7 | 看spring-core-core-annotation …的code |  |  | 劉玠均 | 2023-12-21 | Suspend
W2-8 | 看spring-context的code |  |  | 楊昕叡 | 2023-12-21 | Suspend
W2-9 | 看spring-core-cglib, spring-core-asm的code |  |  | 林俊佑 | 2023-12-21 | Suspend
W1-1 | Survey Spring Boot |  |  | 許庭瑋 | 2023-09-19 | Closed
W1-2 | Survey Spring Cloud |  |  | 陳君翰 | 2023-09-19 | Closed
W1-3 | Survey Spring Framework - Core Container |  |  | 劉玠均 | 2023-09-19 | Closed
W1-4 | Survey Spring Framework - AOP |  |  | 楊昕叡 | 2023-09-19 | Closed
W1-5 | Survey Spring Framework - Data Access/Integration |  |  | 洪世彬 | 2023-09-19 | Closed
W1-6 | Survey Spring Framework - Web (MVC/Remoting) |  |  | 林俊佑 | 2023-09-19 | Closed
W1-7 | Summarize Spring components in the slide |  |  | All | 2023-09-20 20:00 | Closed
W1-8 | Complete AOP slide |  |  | 楊昕叡 | 2023-09-20 20:00 | Closed
W1-9 | Complete ORM / JDBC slide |  |  | 洪世彬 | 2023-09-20 20:00 | Closed

## 1031 (W7)
Group 2 Meeting Minutes
Date |  | 2023-10-30
Time |  | 19:00-20:15
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均、許庭瑋
Objective |  | 討論本週作業、inner class 用途、分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- 組員討論HW的design，分析題意，討論每位design的意見，最後統合大家意見，找出覺得最好的解答 - 討論inner class
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/14mvEN7tcV86A9R4gtCwyWTrLbY_Ak3ybtYkqKbznDW0/edit?usp=sharing
WBS |  | WBS
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | Code tracing: See WBS W7 |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed
2 | Code tracing: See WBS W7 |  |  | 洪世彬 | 2023-11-02 08:00 | Closed
3 | Code tracing: See WBS W7 |  |  | 劉玠均 | 2023-11-02 08:00 | Closed
4 | Code tracing: See WBS W7 |  |  | 楊昕叡 | 2023-11-02 08:00 | Closed
5 | Code tracing: See WBS W7 |  |  | 林俊佑 | 2023-11-02 08:00 | Closed
6 | Code tracing: See WBS W7 |  |  | 陳君翰 | 2023-11-02 08:00 | Closed
7 | Complete weekly slides (code tracing) |  |  | all | 2023-11-02 08:00 | Closed
8 | Homework 0-2 (P83-P85) (jira) |  |  | all | 2023-11-01 20:00 | Closed
9 | Complete inner class slide |  |  | 許庭瑋 | 2023-11-02 08:00 | Closed

## 1024 (W6)
Group 2 Meeting Minutes
Date |  | 2023-10-24
Time |  | 19:30-21:10
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論 JIRA 使用方式、分享 Code tracing 進度
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
- 俊佑、世彬介紹 JIRA 概念與使用方式 (如：如何新增 issues、管理 issues 狀態：Backlog, TO DO, IN PROGRESS, DONE) - 團隊成員分享 Code tracing 進度、討論閱讀到特別的 design patterns 與難理解的部分 - 庭瑋說明 Weekly Progress Report 的書寫方式
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1yBTpDCiO_UuWSCr3CAXGficWpFI-lqzfciQ-FJPA_IM/edit#slide=id.p
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | Code tracing: See WBS W6 |  |  | 許庭瑋 | 2023-10-26 08:00 | Closed
2 | Code tracing: See WBS W6 |  |  | 洪世彬 | 2023-10-26 08:00 | Closed
3 | Code tracing: See WBS W6 |  |  | 劉玠均 | 2023-10-26 08:00 | Closed
4 | Code tracing: See WBS W6 |  |  | 楊昕叡 | 2023-10-26 08:00 | Closed
5 | Code tracing: See WBS W6 |  |  | 林俊佑 | 2023-10-26 08:00 | Closed
6 | Code tracing: See WBS W6 |  |  | 陳君翰 | 2023-10-26 08:00 | Closed
7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-26 08:00 | Closed
8 | 在 JIRA 新增自己的 issues |  |  | all | 2023-10-26 08:00 | Closed

## 1017 (W5)
Group 2 Meeting Minutes
Date |  | N/A
Time |  | N/A
Location |  | N/A
Facilitator |  | N/A
Recorded by |  | 劉玠均
Objective |  | N/A
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant
陳君翰 |  | b07902059@ntu.edu.tw | Participant
洪世彬 |  | p11922005@ntu.edu.tw | Participant
劉玠均 |  | d11922012@ntu.edu.tw | Participant
楊昕叡 |  | b10902002@ntu.edu.tw | Participant
林俊佑 |  | r11922114@ntu.edu.tw | Participant
Meeting Agendas
因code tracing各自看自己的部分，這次沒有交集，經大家同意，本週無會議。庭瑋已生成 Progress Review template，大家填畢即可。
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1NDGVwsHvsW3LLyDNLBcpbC2EGcbR1UFPRx5hSZRNYDc/edit#slide=id.p
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | Code tracing: See WBS W5 |  |  | 許庭瑋 | 2023-10-19 08:00 | Closed
2 | Code tracing: See WBS W5 |  |  | 洪世彬 | 2023-10-19 08:00 | Closed
3 | Code tracing: See WBS W5 |  |  | 劉玠均 | 2023-10-19 08:00 | Closed
4 | Code tracing: See WBS W5 |  |  | 楊昕叡 | 2023-10-19 08:00 | Closed
5 | Code tracing: See WBS W5 |  |  | 林俊佑 | 2023-10-19 08:00 | Closed
6 | Code tracing: See WBS W5 |  |  | 陳君翰 | 2023-10-19 08:00 | Closed
7 | Complete weekly slides (code tracing) |  |  | all | 2023-10-19 08:00 | Open

## 1010 (W4)
Group 2 Meeting Minutes
Date |  | 10/10 19:00-20:00
Time |  | 10/10 19:00-20:00
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論 HW4 & HW5
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Facilitator |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
2023/10/10 - 討論 HW4 & HW5：討論大家各自練習的答案，觀念上有不清楚的地方也可以在會議中提出。 - 更新 WBS 調整進度：Expected Date 要全部估完，組長庭瑋已經加上 Actual Effort & Done 欄位以利紀錄實際時數與是否完成。
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1hSe135v3DbT58SF5p9IOMUHaHVYEbMoNn7IzD-PGQqg/edit#slide=id.g28852f91f42_0_263
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | WBS: 列出到 W13 的時間規劃 |  |  | all | 2023-10-12 08:00 | Closed
2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 12:00 | Closed
3 | Code tracing: AbstractFileResolvingResource.java, ClassPathResource.java, UrlResource.java, ResourceUtils.java |  |  | 許庭瑋 | 2023-10-12 08:00 | Closed
4 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-12 08:00 | Closed
5 | Code tracing: ConvertingComparator<S, T>, DefaultConversionService, 8 default converters |  |  | 劉玠均 | 2023-10-12 08:00 | Closed
6 | Code tracing: AnnotationsScanner.java, AttributeMethods.java |  |  | 楊昕叡 | 2023-10-12 08:00 | Closed
7 | Code tracing: spring-core-cglib |  |  | 林俊佑 | 2023-10-12 08:00 | Closed
8 | Code tracing: aot.generate |  |  | 陳君翰 | 2023-10-12 08:00 | Closed
9 | Complete weekly slides (整合 HW4 & HW5 答案 & code tracing） |  |  | all | 2023-10-12 08:00 | Open

## 0928 (W3)
Group 2 Meeting Minutes
Date |  | 2023/9/28, 2023/10/03
Time |  | 20:00~21:00, 19:00~20:00
Location |  | 線上
Facilitator |  | 劉玠均、許庭瑋
Recorded by |  | 劉玠均
Objective |  | 調整 code tracing 分工、討論
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Facilitator |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
2023/9/28 - 重新訂 code tracing 分工，最後決定以 spring-core-core、spring-core-aot、spring-core-cglib 作為主題。分工如下： - Group 1 (spring-core-core): 庭瑋 (io)、昕叡 (annotation)、玠均 (core+??)、世彬 (others) - Group 2 (spring-core-aot, spring-core-cglib): 俊佑、君翰 - 討論 Issue tracking system 分工。後經組長庭瑋確認只需 survey 一項，改由俊佑 & 世彬負責 JIRA。 - 討論 progress report for periodically review。須由庭瑋確認格式和與 WBS 的差異。 2023/10/03 - code tracing: 討論與分享 code tracing 過程中情況 （如：模組架構差異、code tracing 與畫 class diagram 的困難 )。 - WBS: 討論各模組 WBS 分工情況。團隊提出的 issue 如估計細緻程度與可否修改，須由庭瑋確認後全組再調整。 - Potential risk: 依本週 code tracing 情況，初步列出造成進度延遲的 potential risks，詳見 Risk 欄位。 - Issue tracking system: 俊佑 & 世彬負責完成 JIRA slides
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1LW6Vwt4BHyLPggqzBw1MxAkE_gt2PS9jrE5tkzxBwG0/edit#slide=id.g28712971df0_0_0
Risk
Priority | Description |  |  | Probability | Impacts | Plan
1 | WBS估計誤差 |  |  | 90% | Medium | 動態調整進度
3 | 有人沒看懂 |  |  | 10% | Low | 會議內部合作討論
2 | 有class跟其他file的相關性太大，導致跟預估相差太大 |  |  | 60% | High | 當週開始提出，調整 priority
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | 重新定 code tracing 分工: spring-core-core |  |  | all | 2023-09-28 | Closed
2 | 弄出weekly progress review的template |  |  | 許庭瑋 | 2023-10-12 08:00 | Ongoing
3 | 依新分工調整 WBS (LOC, responsibility, effort) |  |  | all | 2023-10-03 19:00 | Open
4 | Survey issue tracking system |  |  | all | 2023-10-03 19:00 | Closed
5 | 釐清 W4 presentation focus、progress report |  |  | 許庭瑋 | 2023-10-03 19:00 | Closed
6 | 確定 spring-core-core others 細部分工 |  |  | 劉玠均、洪世彬 | 2023-09-29 | Closed
7 | 確定 spring-core-aot, spring-core-cglib 細部分工 |  |  | 林俊佑、陳君翰 | 2023-10-03 | Closed
8 | Code tracing: spring-core-io |  |  | 許庭瑋 | 2023-10-05 08:00 | Closed
9 | Code tracing: org.springframework.core.codec |  |  | 洪世彬 | 2023-10-05 08:00 | Closed
10 | Code tracing: W3 in WBS (i.e., spring-core converter/*.java, GenericConversionService.java) |  |  | 劉玠均 | 2023-10-05 08:00 | Closed
11 | Code tracing:W3 in WBS |  |  | 楊昕叡 | 2023-10-05 08:00 | Closed
12 | Code tracing: spring-core-cglib 內 proxy |  |  | 林俊佑 | 2023-10-05 08:00 | Closed
13 | Code tracing: spring-core-cglib 內 proxy |  |  | 陳君翰 | 2023-10-05 08:00 | Ongoing
14 | Complete JIRA slides |  |  | 林俊佑、洪世彬 | 2023-10-05 08:00 | Closed
15 | Complete weekly slides |  |  | all | 2023-10-05 08:00 | Ongoing

## 0926 (W2)
Group 2 Meeting Minutes
Date |  | 2023-09-23
Time |  | 19:00~20:10
Location |  | 線上
Facilitator |  | 劉玠均
Recorded by |  | 劉玠均
Objective |  | 討論軟體開發流程、完成 Code tracing 的組內分工
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Participant |  |  | v
陳君翰 |  | b07902059@ntu.edu.tw | Participant |  |  | v
洪世彬 |  | p11922005@ntu.edu.tw | Participant |  |  | v
劉玠均 |  | d11922012@ntu.edu.tw | Facilitator |  |  | v
楊昕叡 |  | b10902002@ntu.edu.tw | Participant |  |  | v
林俊佑 |  | r11922114@ntu.edu.tw | Participant |  |  | v
Meeting Agendas
依助教公布作業內容，討論下列議題： - 團隊成員分享開發流程經驗。討論不同流程，如 Waterfall, Rapid Application Development, and Agile 實作上的利弊與權衡。 分享開發流程在不同情境的應用，如：開發流程中的哪個階段導入設計模式。 - 討論 code tracing 方法，如何開始讀程式以提升閱讀效率。
Slides
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1qxH6idP-FLoamuOfQRkGkW7dFU33rLaFJjge9ox3SnU/edit?usp=sharing
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | Code tracing 分工 |  |  | All | 2023-09-24 | Closed
2 | Complete week 2 slide |  |  | All | 2023-09-25 20:00 | Closed
3 | 釐清 WBS 書寫方式 |  |  | 許庭瑋 | 2023-09-28 08:00 | Closed
4 | 看spring-expression的code |  |  | 許庭瑋 | 2023-12-21 | Ongoing
5 | 看spring-core-aot….的code |  |  | 陳君翰 | 2023-12-21 | Ongoing
6 | 看spring-beans的code |  |  | 洪世彬 | 2023-12-21 | Ongoing
7 | 看spring-core-core-annotation …的code |  |  | 劉玠均 | 2023-12-21 | Ongoing
8 | 看spring-context的code |  |  | 楊昕叡 | 2023-12-21 | Ongoing
9 | 看spring-core-cglib, spring-core-asm的code |  |  | 林俊佑 | 2023-12-21 | Ongoing

## 0919
Group 2 Meeting Minutes
Date |  | 2023-09-19
Time |  | 20:00~21:00
Location |  | 線上
Facilitator
Recorded by
Objective |  | 討論要選spring的哪個部分
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw
陳君翰 |  | b07902059@ntu.edu.tw | Participant
洪世彬 |  | p11922005@ntu.edu.tw
劉玠均 |  | d11922012@ntu.edu.tw
楊昕叡 |  | b10902002@ntu.edu.tw
Meeting Agendas
最後因為根據大家的偏好，決定以 Spring Framework - AOP 作為課程研究主題。
Slides
Group |  | Slide URL
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | Summarize Spring Components in the slide |  |  | All | 2023-09-20 20:00 | Open

## 0914 (W1)
Group 2 Meeting Minutes
Date |  | 2023/09/14、2023/09/19
Time |  | 19:00~19:30、20:00~21:00
Location |  | 線上
Facilitator |  | 許庭瑋
Recorded by |  | 許庭瑋
Objective |  | 討論要選spring的哪個部分
Participants
Name |  | E-mail | Role |  |  | Present
許庭瑋 |  | b09902140@ntu.edu.tw | Facilitator
陳君翰 |  | b07902059@ntu.edu.tw | Participant
洪世彬 |  | p11922005@ntu.edu.tw | Participant
劉玠均 |  | d11922012@ntu.edu.tw | Participant
楊昕叡 |  | b10902002@ntu.edu.tw | Participant
林俊佑 |  | r11922114@ntu.edu.tw | Participant
Meeting Agendas
2023/9/14 19:00 ~19:10: 我中午時有問助教一些細節，像是term project的形式、方向、下禮拜要做的事、報告的模式等等。這時我把助教的回復講給其他人聽，讓大家了解我們需要做什麼 2023/9/14 19:10 ~19:30:大家開始討論要選spring framework的哪個部分當作我們的term project，最後決定我們各自挑spring framework的一個部分回去看，之後再來討論。 2023/9/19 20:00 ~20:40:大家各自講說所調查的部分有什麼功能，讓大家可以了解說每個部分所負責的功能是什麼。 2023/9/19 20:40 ~21:00:大家了解各個部份的功能後，根據自己的興趣和背景去決定比較偏好哪些部分。最後選擇了Spring AOP 和 ORM/JDBC 當做我們組的term project。
Slides
Group |  | Slide URL
Group 2 |  | https://docs.google.com/presentation/d/1uDh9K0pvVy6SsEQzohuZj6zmORLQ3qFCQmJ0UKlSKVw/edit#slide=id.p
Action Items
No. | Action Items |  |  | Responsibilty | Deadline | Status
1 | Survey Spring Boot |  |  | 許庭瑋 | 2023-09-19 | Closed
2 | Survey Spring Cloud |  |  | 陳君翰 | 2023-09-19 | Closed
3 | Survey Spring Framework - Core Container |  |  | 劉玠均 | 2023-09-19 | Closed
4 | Survey Spring Framework - AOP |  |  | 楊昕叡 | 2023-09-19 | Closed
5 | Survey Spring Framework - Data Access/Integration |  |  | 洪世彬 | 2023-09-19 | Closed
6 | Survey Spring Framework - Web (MVC/Remoting) |  |  | 林俊佑 | 2023-09-19 | Closed
7 | Summarize Spring components in the slide |  |  | All | 2023-09-20 20:00 | Closed
8 | Complete AOP slide |  |  | 楊昕叡 | 2023-09-20 20:00 | Closed
9 | Complete ORM / JDBC slide |  |  | 洪世彬 | 2023-09-20 20:00 | Closed